	2013 Green Scene Timeline

	

	Monday 1:00 pm
	Cheryl and Martha go to truck rental and finalize order for truck

	

	Monday – Wednesday
	Mary picks up a load of boxes from Martha Haber’s, if possible.

	

	Tuesday – Thursday am
	Be sure EVERY plant has a stick label in the pot before delivering them to Cheryl's. Insert the stick label in the FRONT of the pot facing forward, to make it easier to read.  The plants are so big, we'll never see them if they're in the back of the pot. Members should call Martha Haber if they need any sticks BEFORE taking plants to Cheryl's. Plants can be delivered to Cheryl’s front yard.

	
	

	

	Tuesday afternoon
	Cheryl picks up truck from truck rental

	

	Wednesday am
	Shelving installed in truck.

Cheryl and Brenda drive U-Haul to Vet's Hospital and Martha H's to pick up plants; Martha meets them at venues to assist.

Make a second plant run to Martha Wida’s, Marlene’s, and Brenda’s.

When truck returns to Cheryl's, as many plants as possible are loaded into the truck.

	Wednesday morning or afternoon (TBD)
	

	Wednesday pm OR Thursday am
	

	
	

	

	Wednesday pm
	Ed, Erin, and Roger go to Cheryl’s house to pick up stands using their trucks.

	

	Deadline: 10:00 AM Thursday
	All flats of plants MUST be delivered to Cheryl’s by 10:00 am Thursday morning or the member must take them to the Arboretum. No exceptions.

	

	Thursday, 9:00 am
	Arboretum opens for deliveries through the Maintenance Gate to Space #8.

Construction team arrives at Arboretum to begin assembling stands.

Cheryl drives U-Haul to Arboretum to deliver plants.

Volunteer workers go to arboretum to help unload plants and place them on shelves.

Volunteers are to bring all Green Scene supplies to booth.
Parking on Thursday and Friday is $8 per day per car. PARKING WITHOUT PAYING WILL RESULT IN A CITATION. Parking is free on the weekend.
Lunch and bottled water will be provided for workers on Thursday. 

	
	

	

	Thursday, 11:30 am
	Emily and Sue go buy lunch for workers.

	

	Thursday am
	Cheryl makes second run to pick up remaining plants from her house.

Volunteers unload plants. 

Volunteers continue to arrange plants and set up booth. If we finish the booth on Thursday we do not have to go back on Friday.

	
	

	

	Friday am
	Martha and Cheryl survey booth to ensure it’s ready and looks WONDERFUL.

	

	Saturday, 8:00 - 8:30am
	Shift 1 arrives at Arboretum to work Green Scene - Please be on time for your shift. Workers on Saturday morning have their entry badges.  

	
	

	

	Saturday, 9:00 am
	Arboretum opens and Green Scene begins!

	

	Saturday, 12:00 - 12:30 pm
	Shift 2 arrives at Arboretum to work Green Scene. A club member will be at the entrance gate to give the entry badges to workers on Saturday and Sunday afternoon shifts. Please be on time for your shift.

	

	Saturday, 4:00 pm
	Green Scene closes.


	2013 Green Scene Final Week Timeline

	

	Sunday, 9:00 – 9:30 am
	Shift 1 arrives at Arboretum to work Green Scene. Workers on Sunday morning should already have their entry badges.  

	

	Sunday, 10:00 am
	Green Scene opens.

	

	Sunday, 12:00 – 12:30 pm
	Shift 2 arrives at Arboretum to work Green Scene. A club member will be at the entrance gate to give entry badges to workers. Please be on time for your shift.

	
	

	

	Sunday, 3:00 pm
	Workers start consolidating flats of plants and stacking empty flats.

	

	Sunday, 3:30 pm
	Russ and rest of tear down crew members get in line at Arboretum.

	

	Sunday, 4:00 pm
	Green Scene closes.

Stands are disassembled and all materials are collected for return to storage.

Roger, Ed, and Erin take stands to storage.

Emily collects flats for her church sale.

?? takes flats for Brenda’s charity.

Martha W’s son takes flats to Martha W's for SOS.

	
	

	

	Sunday, 5:30 pm
	Arboretum closes.

	


